## Projects Tracker
All Projects — Status Tracker
Project | Done | In Progress / Pending | Backlog / Not Started | Total Tasks | Overall Completion | Status
AI Agents (Mail Digest) | 23 | 6 | 2 | 31 | 82.49% | On Track
SG Website | 28 | 2 | 0 | 30 | 97.33% | On Track
Food Safety Program | 49 | 13 | 0 | 62 | 88.91% | On Track
C-SAT Survey | 57 | 0 | 8 | 65 | 87.69% | On Track
GPM&I Project | 0 | 77 | 42 | 119 | 43.14% | At Risk
Trio Academy (LMS) Development | 159 | 2 | 0 | 161 | 99.38% | On Track
TOTAL / OVERALL | 316 | 100 | 52 | 468 | 83.16%

## Daily Progress
DAILY PROGRESS DASHBOARD — ALL PROJECTS | [10 empty] | 14-DAY ROLLING WORKLOAD LOG
[11 empty] | Date | Weekday | Starting | Due | Active | Overdue Open
Report Date | 2026-09-10 |  | Weekday | Thursday | [6 empty] | 2026-09-04 | Fri | 0 | 0 | 58 | 20
Portfolio Completion | 83.16% |  | Total Tasks | 468 | [6 empty] | 2026-09-05 | Sat | 0 | 16 | 58 | 20
[11 empty] | 2026-09-06 | Sun | 6 | 2 | 48 | 27
PROJECT ROLLUP FOR REPORT DATE | [10 empty] | 2026-09-07 | Mon | 3 | 6 | 49 | 29
Project | Starting Today | Due Today | Active Today | Overdue Open | Done | In Progress | Not Started | Total Tasks | Completion % | Status | 2026-09-08 | Tue | 2 | 2 | 45 | 31
AI Agents (Mail Digest) | 0 | 0 | 0 | 8 | 23 | 6 | 2 | 31 | 82.49% | On Track | #REF! | #REF! | 0 | 0 | 0 | 0
SG Website Plan | 0 | 0 | 0 | 2 | 28 | 2 | 0 | 30 | 97.33% | On Track | #REF! | #REF! | 0 | 0 | 0 | 0
Food Safety Program | 0 | 0 | 0 | 17 | 49 | 17 | 0 | 66 | 85.8% | On Track | #REF! | #REF! | 0 | 0 | 0 | 0
C-SAT Survey | 0 | 7 | 42 | 0 | 57 | 0 | 8 | 65 | 87.69% | On Track | #REF! | #REF! | 0 | 0 | 0 | 0
GPM&I Project Plan | 3 | 2 | 3 | 7 | 0 | 72 | 40 | 112 | 42.86% | At Risk | #REF! | #REF! | 0 | 0 | 0 | 0
Trio Academy(LMS) | 0 | 0 | 0 | 2 | 159 | 2 | 0 | 161 | 99.38% | On Track | #REF! | #REF! | 0 | 0 | 0 | 0
TOTAL / OVERALL | 3 | 9 | 45 | 36 | 316 | 99 | 50 | 465 | 67.96% | On Track | #REF! | #REF! | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | 0 | 0 | 0 | 0
TASK DETAIL — ACTIVE ON REPORT DATE + OVERDUE OPEN ITEMS | [12 empty] | 0 | 0 | 0 | 0
Project | Task | Resp | Start Date | End Date | Done % | Day Flag | Days to Due
AI Agents (Mail Digest) | T15 User acceptance test of live /digest command | IA | 2026-08-15 | 2026-08-25 | 42.86% | OVERDUE | -16
AI Agents (Mail Digest) | T25 Create SMTP credential in n8n | IA | 2026-08-25 | 2026-09-05 | 42.86% | OVERDUE | -5
AI Agents (Mail Digest) | T26 Create Telegram credential for @hemaminibot | IA | 2026-08-25 | 2026-09-05 | 42.86% | OVERDUE | -5
AI Agents (Mail Digest) | T27 Wire new credentials into workflow nodes | IA | 2026-08-25 | 2026-09-05 | 42.86% | OVERDUE | -5
AI Agents (Mail Digest) | T28 Activate all three n8n workflows | IA | 2026-08-25 | 2026-09-05 | 42.86% | OVERDUE | -5
AI Agents (Mail Digest) | T29 Live-verify Mail Capture field mapping | IA | 2026-08-25 | 2026-09-05 | 42.86% | OVERDUE | -5
AI Agents (Mail Digest) | T30 Add Telegram command routing (/high /search /read) | IA | 2026-08-25 | 2026-09-05 | 0% | OVERDUE | -5
AI Agents (Mail Digest) | T31 Add Data Table retention/cleanup | IA | 2026-08-25 | 2026-09-05 | 0% | OVERDUE | -5
SG Website Plan | Get Proc Content Writing | IA - MM | 2026-08-10 | 2026-08-12 | 40% | OVERDUE | -29
SG Website Plan | Get SS&C Content Writing | IA - MM | 2026-08-10 | 2026-08-12 | 80% | OVERDUE | -29
Food Safety Program | LMS Marketing Campain | MAS - IA -MM | 2026-07-25 | 2026-09-01 | 62.5% | OVERDUE | -9
Food Safety Program | * Launch Site Competition | IA | 2026-08-01 | 2026-08-05 | 62.5% | OVERDUE | -36
Food Safety Program | * Announce Best Performing Site | IA | 2026-08-20 | 2026-08-30 | 62.5% | OVERDUE | -11
Food Safety Program | * Design Digital Certificates & Badges | IA | 2026-08-20 | 2026-08-30 | 62.5% | OVERDUE | -11
Food Safety Program | Generate Exam Certificate | IA - MM | 2026-08-09 | 2026-08-14 | 62.5% | OVERDUE | -27
Food Safety Program | المظهر الشخصى والنظافه الشخصيه: | MAS - IA - MM | 2026-07-11 | 2026-07-12 | 37.5% | OVERDUE | -60
Food Safety Program | الاجراءات المتبعه لاستخدام و معايرة الترمومترات | MAS - IA - MM | 2026-07-17 | 2026-07-18 | 37.5% | OVERDUE | -54
Food Safety Program | اجراء تشغيلى خاص بتتبع حاله حرجه | MAS - IA - MM | 2026-07-17 | 2026-07-18 | 37.5% | OVERDUE | -54
Food Safety Program | اجراء التخلص من منتج به اصابه حشريه | MAS - IA - MM | 2026-07-19 | 2026-07-20 | 37.5% | OVERDUE | -52
Food Safety Program | start implementation | IA | 2026-07-07 | 2026-07-11 | 37.5% | OVERDUE | -61
Food Safety Program | Review on every activity line to ensure alignment with agreed upon plan | MAS - MM | 2026-07-07 | 2026-07-21 | 37.5% | OVERDUE | -51
Food Safety Program | Aopproval | MAS | 2026-07-20 | 2026-07-21 | 37.5% | OVERDUE | -51
Food Safety Program | Posting/rollout | MAS - IA | 2026-07-07 | 2026-07-22 | 37.5% | OVERDUE | -50
Food Safety Program | Design Prepare Exam Photo | IA | 2026-08-24 | 2026-08-25 | 75% | OVERDUE | -16
Food Safety Program | Design Entry Level Photo | IA | 2026-08-24 | 2026-08-25 | 25% | OVERDUE | -16
Food Safety Program | Design Supervisor Level Photo | IA | 2026-08-24 | 2026-08-25 | 25% | OVERDUE | -16
Food Safety Program | Design Managerial Level Photo | IA | 2026-08-24 | 2026-08-25 | 25% | OVERDUE | -16
C-SAT Survey | Analysis Each site alone | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | * Survey Interface & Worker UX | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Build 1-10 rating scale UI with color-coded guidance (1-3 unsatisfied, 4-8 satisfied, 9-10 excellent) | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Program the 12 approved quality criteria (meal quality, taste, quantity, variety, temperature, cleanliness, staff, speed, packaging, hall cleanliness, meal timing, overall satisfaction) | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Full mobile & touchscreen responsive support for field devices | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Full Arabic (RTL) language support with correct number ordering | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Optional notes fields for worker name, suggestions and complaints with timestamp | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | * Executive Admin Dashboard | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Live KPI dashboard: overall CSAT, average score, Promoters/Passives/Detractors classification | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Interactive D3 arc gauge for real-time satisfaction % vs. target | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Side-by-side dual branch/factory comparison tool | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Critical alert system: auto-flag ratings below 6.0 with acknowledge/follow-up action | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Advanced date & site filters (today, yesterday, last 7/30 days, this month, custom range) | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | * Gemini AI Deep-Dive Analytics | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Backend integration with Google Gemini for periodic executive summary of all worker feedback | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Automated sentiment & root-cause classification of complaints/suggestions by service theme and priority | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Auto-generated corrective action list for kitchen & food service teams | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | * Site Management & Access Control | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Create and manage branches/factories with activate/deactivate toggle and instant save | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Active/Inactive site filter tabs for large factory rollouts | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Bulk site import via JSON/CSV/plain text with duplicate validation | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Custom QR code generator & PNG downloader for each site, print-ready for dining halls | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Randomized encrypted survey links (UUID) per site with Rotate UUID button to prevent guessing | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | * Reporting & Export Engine | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Export formal Word reports (.docx) with org structure, AI summary and branch comparison table | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Export formatted print-ready PDF reports (.pdf) for management meetings | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Export raw survey data (.csv / Excel) for statistical analysis | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | * Security & Production Hardening | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Brute-force protection: auto-lock login for 30 seconds after 5 failed attempts | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Removed autofill/autosave of passwords and secured default admin account | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Input sanitization (XSS) for name and notes fields against malicious code/tags | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Honeypot bot trap field to block fake/automated survey submissions | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Offline & PWA support via Service Worker with local caching and Firebase Firestore sync | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Multi-layer logo fallback system (transparent image, embedded encoding, pure SVG) for all production environments | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | ** Comprehensive project documentation (README.md) covering setup, build and deployment | IA-MH | 2026-08-15 | 2026-09-15 | 100% | IN PROGRESS | 5
C-SAT Survey | * Next Phase / Future Roadmap | 0 | 2026-08-26 | 2026-09-10 | 0% | DUE TODAY | 0
C-SAT Survey | ** [High Priority] Automated notifications (Email/WhatsApp) to site manager & quality supervisor on critical rating below 4/10 for immediate action during meal service | IA-MH | 2026-08-26 | 2026-09-10 | 0% | DUE TODAY | 0
C-SAT Survey | ** [High Priority] Multi-role user permissions (RBAC): Super Admin (all branches), Site Manager (own branch only), Quality Auditor (reports only) | IA-MH | 2026-08-26 | 2026-09-10 | 0% | DUE TODAY | 0
C-SAT Survey | ** [Medium Priority] Meal shift classification filter (breakfast/lunch/dinner/suhoor/dry ration) to analyze quality per work shift | IA-MH | 2026-08-26 | 2026-09-10 | 0% | DUE TODAY | 0
C-SAT Survey | ** [Medium Priority] Photo upload with survey complaints so workers can attach a picture of the meal/dish to document issues for central kitchen teams | IA-MH | 2026-08-26 | 2026-09-10 | 0% | DUE TODAY | 0
C-SAT Survey | ** [Enhancement] Scheduled executive digest: automated weekly/monthly PDF summary report emailed to Trio Catering senior management | IA-MH | 2026-08-26 | 2026-09-10 | 0% | DUE TODAY | 0
C-SAT Survey | ** [Enhancement] Additional language support (Arabic / English / Urdu / Hindi) in survey interface to cover expatriate workforce at factories and sites | IA-MH | 2026-08-26 | 2026-09-10 | 0% | DUE TODAY | 0
GPM&I Project Plan | 1 | MAS & MM & IA | MAS & MM & IA | 2026-09-07 | 0% | OVERDUE | -3
Trio Academy(LMS) | Create Certificate Template for Food Safety | IA | 2026-09-06 | 2026-09-06 | 60% | OVERDUE | -4
Trio Academy(LMS) | Optimize Certificate Page and Backend | IA | 2026-09-06 | 2026-09-06 | 40% | OVERDUE | -4
Formulas:
Date = [Date, row above]+1
Note on B3: Ibrahim: Input cell — change this date to re-run the whole dashboard for any day.

## C-SAT Survey
C-SaT Survay Project Plan 24/08/2026 |  |  |  |  | Progress | [7 empty] | STATUS SUMMARY
S | C-SaT Survay | Resp | Start Date | End Date | Project concept approval | Project paln & approval | Implementaion | [5 empty] | Done | 57 | 87.69%
[7 empty] | CEO | AI | IT | OPS | Missing | Done | In progress / Pending | 0 | 0%
| Planning & Setup |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  |  | Backlog / Not started | 8 | 12.31%
1 | Planning for Implementation | IA-MH | 2026-07-28 | 2026-07-29 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Overall completion | 87.69%
2 | Creating Google Forms | IA-MH | 2026-07-29 | 2026-07-29 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Total tasks | 65
3 | Review | IA-MH-MAS | 2026-07-29 | 2026-07-30 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
4 | Generate QR for Forms | IA-MH | 2026-07-29 | 2026-07-30 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
5 | Test Forms with QR code | IA-MH-MM-AM | 2026-07-29 | 2026-07-30 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
6 | Deliver QR code | IA-MH | 2026-07-30 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
| Site Rollout (Client Deployments) |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
7 | * MARS | IA-MH | 2026-07-31 | 2026-08-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
8 | * EDITA: | IA-MH | 2026-08-01 | 2026-08-07 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
9 | ** EDITA-6 | IA-MH | 2026-08-02 | 2026-08-02 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
10 | ** EDITA-7 | IA-MH | 2026-08-03 | 2026-08-03 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
11 | ** EDITA-8 | IA-MH | 2026-08-04 | 2026-08-04 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
12 | ** EDITA-9 | IA-MH | 2026-08-05 | 2026-08-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
13 | ** EDITA-10 | IA-MH | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
14 | ** EDITA-15 | IA-MH | 2026-08-07 | 2026-08-07 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
15 | * MONDELEZ: | IA-MH | 2026-08-08 | 2026-08-11 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
16 | ** MONDELEZ BEA | IA-MH | 2026-08-09 | 2026-08-09 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
17 | ** MONDELEZ C-TOR | IA-MH | 2026-08-10 | 2026-08-10 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
18 | ** MONDELEZ B-TOR | IA-MH | 2026-08-11 | 2026-08-11 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
19 | * BALL | IA-MH | 2026-08-12 | 2026-08-12 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
20 | * IFF | IA-MH | 2026-08-13 | 2026-08-13 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
21 | * ASTRAZINCA | IA-MH | 2026-08-14 | 2026-08-14 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
22 | * PEPSI TANTA | IA-MH | 2026-08-15 | 2026-08-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
| Analysis & Design (UX/Survey Interface) |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
23 | Analysis Each site alone | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
24 | * Survey Interface & Worker UX | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
25 | ** Build 1-10 rating scale UI with color-coded guidance (1-3 unsatisfied, 4-8 satisfied, 9-10 excellent) | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
26 | ** Program the 12 approved quality criteria (meal quality, taste, quantity, variety, temperature, cleanliness, staff, speed, packaging, hall cleanliness, meal timing, overall satisfaction) | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
27 | ** Full mobile & touchscreen responsive support for field devices | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
28 | ** Full Arabic (RTL) language support with correct number ordering | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
29 | ** Optional notes fields for worker name, suggestions and complaints with timestamp | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
| Admin Dashboard & Analytics |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
30 | * Executive Admin Dashboard | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
31 | ** Live KPI dashboard: overall CSAT, average score, Promoters/Passives/Detractors classification | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
32 | ** Interactive D3 arc gauge for real-time satisfaction % vs. target | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
33 | ** Side-by-side dual branch/factory comparison tool | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
34 | ** Critical alert system: auto-flag ratings below 6.0 with acknowledge/follow-up action | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
35 | ** Advanced date & site filters (today, yesterday, last 7/30 days, this month, custom range) | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
36 | * Gemini AI Deep-Dive Analytics | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
37 | ** Backend integration with Google Gemini for periodic executive summary of all worker feedback | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
38 | ** Automated sentiment & root-cause classification of complaints/suggestions by service theme and priority | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
39 | ** Auto-generated corrective action list for kitchen & food service teams | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
| Site Management & Access Control |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
40 | * Site Management & Access Control | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
41 | ** Create and manage branches/factories with activate/deactivate toggle and instant save | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
42 | ** Active/Inactive site filter tabs for large factory rollouts | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
43 | ** Bulk site import via JSON/CSV/plain text with duplicate validation | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
44 | ** Custom QR code generator & PNG downloader for each site, print-ready for dining halls | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
45 | ** Randomized encrypted survey links (UUID) per site with Rotate UUID button to prevent guessing | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
| Reporting & Export |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
46 | * Reporting & Export Engine | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
47 | ** Export formal Word reports (.docx) with org structure, AI summary and branch comparison table | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
48 | ** Export formatted print-ready PDF reports (.pdf) for management meetings | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
49 | ** Export raw survey data (.csv / Excel) for statistical analysis | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
| Security & Production Hardening |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
50 | * Security & Production Hardening | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
51 | ** Brute-force protection: auto-lock login for 30 seconds after 5 failed attempts | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
52 | ** Removed autofill/autosave of passwords and secured default admin account | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
53 | ** Input sanitization (XSS) for name and notes fields against malicious code/tags | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
54 | ** Honeypot bot trap field to block fake/automated survey submissions | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
55 | ** Offline & PWA support via Service Worker with local caching and Firebase Firestore sync | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
56 | ** Multi-layer logo fallback system (transparent image, embedded encoding, pure SVG) for all production environments | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
57 | ** Comprehensive project documentation (README.md) covering setup, build and deployment | IA-MH | 2026-08-15 | 2026-09-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
| Future Roadmap |  |  |  | FALSE | [5 empty] | 100% | 0%
58 | * Next Phase / Future Roadmap |  | 2026-08-26 | 2026-09-10 | FALSE | [5 empty] | 100% | 0%
59 | ** [High Priority] Automated notifications (Email/WhatsApp) to site manager & quality supervisor on critical rating below 4/10 for immediate action during meal service | IA-MH | 2026-08-26 | 2026-09-10 | FALSE | [5 empty] | 100% | 0%
60 | ** [High Priority] Multi-role user permissions (RBAC): Super Admin (all branches), Site Manager (own branch only), Quality Auditor (reports only) | IA-MH | 2026-08-26 | 2026-09-10 | FALSE | [5 empty] | 100% | 0%
61 | ** [Medium Priority] Meal shift classification filter (breakfast/lunch/dinner/suhoor/dry ration) to analyze quality per work shift | IA-MH | 2026-08-26 | 2026-09-10 | FALSE | [5 empty] | 100% | 0%
62 | ** [Medium Priority] Photo upload with survey complaints so workers can attach a picture of the meal/dish to document issues for central kitchen teams | IA-MH | 2026-08-26 | 2026-09-10 | FALSE | [5 empty] | 100% | 0%
63 | ** [Enhancement] Scheduled executive digest: automated weekly/monthly PDF summary report emailed to Trio Catering senior management | IA-MH | 2026-08-26 | 2026-09-10 | FALSE | [5 empty] | 100% | 0%
64 | ** [Enhancement] Additional language support (Arabic / English / Urdu / Hindi) in survey interface to cover expatriate workforce at factories and sites | IA-MH | 2026-08-26 | 2026-09-10 | FALSE | [5 empty] | 100% | 0%

## GPM&I
| GPM&I Project Plan 07/09/2026 |  |  |  |  | Progress | [6 empty] | STATUS SUMMARY
| S | GPM&I | Resp | Start Date | End Date | Project concept approval | Project paln & approval | Implementaion |  |  |  |  | Done | 0 | 0%
M / Hrs. | [7 empty] | CEO | AI | FUP | Missing | Done | In progress / Pending | 77 | 64.71%
8 | 1 | مقدمة واستراتيجية الشركة (سلايد 1–8) | MAS & MM & IA | 2026-09-07 | 2026-09-09 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0% | Backlog / Not started | 42 | 35.29%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-09-07 | 2026-09-07 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0% | Overall completion | 0.43137
1 |  | توليد الفيديو (Generate Video) | IA | 2026-09-07 | 2026-09-07 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0% | Total tasks | 119
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-09-08 | 2026-09-08 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67% | Overall completion | 43.14%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-09-08 | 2026-09-08 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0% | Total tasks | 119
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-09-09 | 2026-09-09 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-09-09 | 2026-09-09 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
8 | 2 | مقدمة عن GPM&I ودورة الأداء (سلايد 9–13) | MAS & MM & IA | 2026-09-10 | 2026-09-12 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-09-10 | 2026-09-10 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-09-10 | 2026-09-10 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-09-11 | 2026-09-11 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-09-11 | 2026-09-11 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-09-12 | 2026-09-12 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-09-12 | 2026-09-12 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
8 | 3 | مرحلة التخطيط للأداء (سلايد 14–17) | MAS & MM & IA | 2026-09-13 | 2026-09-15 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-09-13 | 2026-09-13 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-09-13 | 2026-09-13 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-09-14 | 2026-09-14 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-09-14 | 2026-09-14 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-09-15 | 2026-09-15 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-09-15 | 2026-09-15 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
8 | 4 | تمرين SMARTER + BSC/KPIs (سلايد 18–21) | MAS & MM & IA | 2026-09-16 | 2026-09-18 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-09-16 | 2026-09-16 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-09-16 | 2026-09-16 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-09-17 | 2026-09-17 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-09-17 | 2026-09-17 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-09-18 | 2026-09-18 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-09-18 | 2026-09-18 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
8 | 5 | أمثلة KPIs ووصف وظيفي - مدير سلامة الغذاء (سلايد 22–26) | MAS & MM & IA | 2026-09-19 | 2026-09-21 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-09-19 | 2026-09-19 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-09-19 | 2026-09-19 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-09-20 | 2026-09-20 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-09-20 | 2026-09-20 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-09-21 | 2026-09-21 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-09-21 | 2026-09-21 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
8 | 6 | أمثلة مستويات أداء قياسية (سلايد 27–28) | MAS & MM & IA | 2026-09-22 | 2026-09-24 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-09-22 | 2026-09-22 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-09-22 | 2026-09-22 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-09-23 | 2026-09-23 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-09-23 | 2026-09-23 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-09-24 | 2026-09-24 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-09-24 | 2026-09-24 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
8 | 7 | مرحلة التنفيذ: سجل الأحداث واجتماعات المراجعة (سلايد 29–33) | MAS & MM & IA | 2026-09-25 | 2026-09-27 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-09-25 | 2026-09-25 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-09-25 | 2026-09-25 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-09-26 | 2026-09-26 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-09-26 | 2026-09-26 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-09-27 | 2026-09-27 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-09-27 | 2026-09-27 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
8 | 8 | التوجيه الفعال ODSEAF + تمارين Role Play (سلايد 34–37) | MAS & MM & IA | 2026-09-28 | 2026-09-30 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-09-28 | 2026-09-28 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-09-28 | 2026-09-28 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-09-29 | 2026-09-29 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-09-29 | 2026-09-29 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-09-30 | 2026-09-30 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-09-30 | 2026-09-30 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
8 | 9 | الإعداد لعملية التقييم النهائي (سلايد 38–42) | MAS & MM & IA | 2026-10-01 | 2026-10-03 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-10-01 | 2026-10-01 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-10-01 | 2026-10-01 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-10-02 | 2026-10-02 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-10-02 | 2026-10-02 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-10-03 | 2026-10-03 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-10-03 | 2026-10-03 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
8 | 10 | تقييم الأداء وأخطاؤه الشائعة (سلايد 43–47) | MAS & MM & IA | 2026-10-04 | 2026-10-06 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-10-04 | 2026-10-04 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-10-04 | 2026-10-04 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-10-05 | 2026-10-05 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-10-05 | 2026-10-05 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-10-06 | 2026-10-06 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-10-06 | 2026-10-06 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
8 | 11 | نماذج الوظائف حسب المستوى E (سلايد 47–53) | MAS & MM & IA | 2026-10-07 | 2026-10-09 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-10-07 | 2026-10-07 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-10-07 | 2026-10-07 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-10-08 | 2026-10-08 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-10-08 | 2026-10-08 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-10-09 | 2026-10-09 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-10-09 | 2026-10-09 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
8 | 12 | نماذج الوظائف حسب المستوى M (Job Models – Level M) | MAS & MM & IA | 2026-10-10 | 2026-10-12 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-10-10 | 2026-10-10 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-10-10 | 2026-10-10 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-10-11 | 2026-10-11 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-10-11 | 2026-10-11 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-10-12 | 2026-10-12 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-10-12 | 2026-10-12 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
8 | 13 | نماذج الوظائف حسب المستوى S (Job Models – Level S) | MAS & MM & IA | 2026-10-13 | 2026-10-15 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-10-13 | 2026-10-13 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-10-13 | 2026-10-13 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-10-14 | 2026-10-14 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-10-14 | 2026-10-14 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-10-15 | 2026-10-15 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-10-15 | 2026-10-15 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
8 | 14 | نموذج الجدارات وتقييمها (سلايد 72–76) | MAS & MM & IA | 2026-10-16 | 2026-10-18 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-10-16 | 2026-10-16 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-10-16 | 2026-10-16 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-10-17 | 2026-10-17 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-10-17 | 2026-10-17 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-10-18 | 2026-10-18 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-10-18 | 2026-10-18 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
8 | 15 | المعايرة Calibration ولجنة المراجعة (سلايد 77–80) | MAS & MM & IA | 2026-10-19 | 2026-10-21 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-10-19 | 2026-10-19 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-10-19 | 2026-10-19 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-10-20 | 2026-10-20 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-10-20 | 2026-10-20 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-10-21 | 2026-10-21 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-10-21 | 2026-10-21 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
8 | 16 | منحنى التوزيع الطبيعي Forced Distribution (NDC) | MAS & MM & IA | 2026-10-22 | 2026-10-24 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-10-22 | 2026-10-22 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-10-22 | 2026-10-22 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-10-23 | 2026-10-23 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-10-23 | 2026-10-23 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-10-24 | 2026-10-24 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-10-24 | 2026-10-24 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
8 | 17 | BSC لكل الإدارات (سلايد 82–88) | MAS & MM & IA | 2026-10-25 | 2026-10-27 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
0.5 |  | إعداد البرومبت (Prepare Prompt) | IA & MM | 2026-10-25 | 2026-10-25 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
1 |  | توليد الفيديو (Generate Video) | IA | 2026-10-25 | 2026-10-25 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
3 |  | مونتاج الفيديو (Edit Video) | IA | 2026-10-26 | 2026-10-26 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
2 |  | مراجعة الفيديو (Review Video) | MAS & MM | 2026-10-26 | 2026-10-26 | TRUE | TRUE | FALSE | FALSE | FALSE | 100% | 0%
0.5 |  | الرفع على Bunny (Upload to Bunny) | IA | 2026-10-27 | 2026-10-27 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%
1 |  | المزامنة مع Trio Academy (Sync with Trio Academy) | IA | 2026-10-27 | 2026-10-27 | TRUE | TRUE | TRUE | FALSE | TRUE | 33.33% | 66.67%

## AI Agents
Mail Digest AI Agent — Project Plan 24/08/2026 |  |  |  |  | Progress
S | Mail Digest AI Agent | Resp | Start Date | End Date | Design / Spec | Build | Delivery
[7 empty] | Config | Test | Deploy | Verify | Docs | Missing | Done
1 | PHASE 1 — Local IMAP Tool (this machine)
2 | T01 Build core IMAP client (mail.py) | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | STATUS SUMMARY
3 | T02 Build setup wizard (setup.py) | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Done | 23 | 74.19%
4 | T03 Write project docs (CLAUDE.md, README.md) | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | In progress / Pending | 6 | 19.35%
5 | T04 Configure real mailbox credentials (.env) | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Backlog / Not started | 2 | 6.452%
6 | T05 Verify live IMAP connection | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Overall completion | 82.49%
7 | T06 Build daily digest engine (digest.py) | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Total tasks | 31
8 | T07 Fix --json flag argparse bug | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
9 | T08 Install Windows scheduled task (10:00 daily) | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
10 | T09 Decide send-every-day vs only-if-new-mail | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
11 | T10 Build Telegram bot (telegram_bot.py) | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
12 | T11 Fix pythonw stdout=None crash | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
13 | T12 Register bot as background service | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
14 | T13 Wire Telegram /digest to also email Outlook | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
15 | T14 Redesign digest format (priority buckets + links) | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
16 | T15 User acceptance test of live /digest command | IA | 2026-08-15 | 2026-08-25 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 57.14% | 42.86%
17 | PHASE 2 — n8n Cloud Migration (n8n.dawrly.space)
18 | T16 Connect to n8n instance | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
19 | T17 Investigate n8n IMAP node capabilities | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
20 | T18 Design capture + buffer + digest architecture | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
21 | T19 Create IMAP credential in n8n | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
22 | T20 Generate n8n API key | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
23 | T21 Create "mail-digest-inbox" Data Table | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
24 | T22 Build "Mail Capture" workflow | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
25 | T23 Build "Daily Digest 10AM" workflow | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
26 | T24 Build "Telegram Command Bot" workflow | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
27 | T25 Create SMTP credential in n8n | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 57.14% | 42.86%
28 | T26 Create Telegram credential for @hemaminibot | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 57.14% | 42.86%
29 | T27 Wire new credentials into workflow nodes | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 57.14% | 42.86%
30 | T28 Activate all three n8n workflows | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 57.14% | 42.86%
31 | T29 Live-verify Mail Capture field mapping | IA | 2026-08-25 | 2026-09-05 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 57.14% | 42.86%
32 | T30 Add Telegram command routing (/high /search /read) | IA | 2026-08-25 | 2026-09-05 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
33 | T31 Add Data Table retention/cleanup | IA | 2026-08-25 | 2026-09-05 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%

## AI Projects Plan (hidden)
AI Projects Plan 04/07/2026 | [5 empty] | Progress | [13 empty] | STATUS SUMMARY
S | Project/Activity | Priority | Resp | Start Date | End Date | Project concept approval | Project paln & approval | Kick-off meeting | Implementaion | [10 empty] | Done | 2 | 5.556%
[9 empty] | BOD | Int Audit | EC/CEO | Fin | SC | OPS | HR | FS | Consult. | Missing | Done | In progress / Pending | 1 | 2.778%
1 | Building the Learning Management System | A+++ | IA&MAS& MM |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Backlog / Not started | 33 | 91.67%
2 | LMS Food Safety Standards Project | A+++ | IA&MAS |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Overall completion | 6.713%
11 | LMS OPS Manual Project | A+++ | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0% | Total tasks | 36
3 | Company functional Gap analysisi | A+++ | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
4 | Competition analysis | A+++ | Ibrahim |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 58.33% | 41.67%
5 | Company Systems (EPM&I) Training | A+++ | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
6 | Customer Relationship Management | A+++ | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
7 | Customer Service Training - Critical Elements of Customer Service | A+++ | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
8 | Customer Service Training - Managing Customer Service | A+++ | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
9 | EPM&I Mgmt and Tracking | A+++ | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
10 | AI Agents | A+++ | Ibrahim |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
12 | The Professional Supervisor | A+++ | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
13 | support OPS | A+++ | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
14 | support HR | A+++ | IA&MAM |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
15 | support Pur | A+++ | IA&HH |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
16 | support WH | A+++ | IA&HH |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Communication Skills | A | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Communication Strategies | A | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Business Leadership - Becoming Mgmt Material | A | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Coaching - A Leadership Skill | A | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Leadership Skills for Supervisors - Communication, Coaching, and Conflict | A | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| The ABC's of Supervising Others | A | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Time Management - Get Organized for Peak Performance | A | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Meeting Management - The Art of Making Meetings Work | A | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Employee Accountability | A | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| MBTI and assessment centers | A | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Purchase the VPS on Hostinger($95.62/first year) and Creator Plan on Heygen(29$/mo) |  | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Setup the server and upload the full LMS |  | Ibrahim |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Stress Management |  | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Accounting Skills for New Supervisors |  | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Team Building - Developing High Performance Teams |  | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Teamwork - Building Better Teams |  | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Inventory Management - The Nuts and Bolts |  | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Delegation - The Art of Delegating Effectively |  | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Motivation Training - Motivating Your Workforce |  | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%
| Intro to Artificiel Intelligence |  | IA&MAS |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 100% | 0%

## SG Website Plan
SG Website 24/08/2026 |  |  |  |  | Progress
S | SG Webiste Project | Resp | Start Date | End Date | Project concept approval | Project paln & approval | Implementaion
[7 empty] | CEO | AI | FUP | Missing | Done
| Planning & Setup | [10 empty] | STATUS SUMMARY
1 | Planning & Determine Goals | IA - MM | 2026-08-08 | 2026-08-09 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Done | 28 | 93.33%
2 | Get Hostigator Credentials | AE | 2026-08-08 | 2026-08-09 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | In progress / Pending | 2 | 6.667%
| Branding & Design | [10 empty] | Backlog / Not started | 0 | 0%
3 | Desgining Logo | IA | 2026-08-08 | 2026-08-09 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Overall completion | 97.33%
4 | Create Branding: | IA | 2026-08-09 | 2026-08-10 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Total tasks | 30
5 | * Branding Book | IA | 2026-08-08 | 2026-08-10 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
6 | * Logo with Background removal | IA | 2026-08-09 | 2026-08-09 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
7 | * Color Palette | IA | 2026-08-09 | 2026-08-09 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
UI Design
8 | Design UI For Desktop | IA | 2026-08-13 | 2026-08-16 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
9 | Design UI For Phone | IA | 2026-08-13 | 2026-08-16 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
Content Writing
10 | Get Soliman Group Content Writing | IA - MM | 2026-08-10 | 2026-08-12 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
11 | Get Trio Catering Content Writing | IA - MM | 2026-08-10 | 2026-08-12 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
12 | Get Trio Café(In Premesis) Content Writing | IA - MM | 2026-08-10 | 2026-08-12 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
13 | Get Trio Academy Content Writing | IA - MM | 2026-08-10 | 2026-08-12 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
14 | Get Trio The Cloud Chefs Content Writing | IA - MM | 2026-08-10 | 2026-08-12 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
15 | Get Trio Events Content Writing | IA - MM | 2026-08-10 | 2026-08-12 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
16 | Get EFS Content Writing | IA - MM | 2026-08-10 | 2026-08-12 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
17 | Get Proc Content Writing | IA - MM | 2026-08-10 | 2026-08-12 | TRUE | TRUE | FALSE | FALSE | FALSE | 60% | 40%
18 | Get SS&C Content Writing | IA - MM | 2026-08-10 | 2026-08-12 | TRUE | TRUE | TRUE | TRUE | FALSE | 20% | 80%
Development & Coding
19 | Start Coding | IA | 2026-08-17 | 2026-08-20 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
20 | feat: implement foundational brand pages, layouts, and motion components for the Soliman Group website | IA | 2026-08-23 | 2026-08-23 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
21 | feat: implement brand and corporate page layouts, section components, and motion-enhanced UI elements | IA | 2026-08-20 | 2026-08-20 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
22 | feat: implement Trio Catering content, mobile navigation components, and immersive home hero section | IA | 2026-08-16 | 2026-08-16 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
23 | perf: cut image weight, throttle 3D scene, defer video preload | IA | 2026-08-13 | 2026-08-13 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
Reviews (QA Checkpoints)
24 | Review | MAS - MM | 2026-08-10 | 2026-08-10 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
25 | Review | MAS - MM | 2026-08-16 | 2026-08-17 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
26 | Review | MAS - MM | 2026-08-20 | 2026-08-21 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
Deployment & Launch
27 | Upload Website to Server | IA | 2026-08-21 | 2026-08-23 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
28 | feat: add HostGator deployment automation script and requirement documentation | IA | 2026-08-17 | 2026-08-17 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
Post-Launch Updates
29 | Update website based on requirements | IA | 2026-08-15 | 2026-08-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
30 | feat: add Trio Catering managed by EFS image asset | IA | 2026-08-23 | 2026-08-23 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%

## Food Safety Program
AI Projects Plan 24/08/2026 |  |  |  |  | Progress | [9 empty] | STATUS SUMMARY
S | LMS Food Safety Standards Project | Resp | Start Date | End Date | Project concept approval | Project paln & approval | Implementaion | [7 empty] | Done | 49 | 79.03%
[7 empty] | CEO | AI | HR | FS | OPS | FUP | Missing | Done | In progress / Pending | 13 | 20.97%
1 | Review SOPs material | MAS - MM - DR.A | 2026-06-04 | 2026-07-04 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Backlog / Not started | 0 | 0%
2 | Approve SOPs material | MAS | 2026-07-04 | 2026-07-04 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Overall completion | 88.91%
3 | Purchase LMS Requirements | MAS - MM - F | 2026-07-04 | 2026-07-06 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Total tasks | 62
4 | Upload LMS and Setup on the Server | IA | 2026-07-05 | 2026-07-08 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
5 | Initialize the Full website and Create All Employee Accounts | IA | 2026-07-07 | 2026-07-10 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
6 | Agree on concept of video presenter with side slide of info in writing | MAS - IA - MM | 2026-07-07 | 2026-07-10 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
7 | Agree on the right tool to make the video | MAS&IA | 2026-07-07 | 2026-07-10 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
8 | Create All Employee Accounts | IA | 2026-07-23 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
9 | Update Exam Security | IA | 2026-07-22 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
10 | Food Safety Exam | IA | 2026-07-22 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
12 | Present LMS | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
12.3636 | Enhance Report page to track Employee | IA | 2026-07-27 | 2026-08-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
13.4091 | * Overview & Compliance | IA | 2026-07-27 | 2026-08-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
14.4545 | * Employee Directory | IA | 2026-07-27 | 2026-08-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
15.5 | * Course Performance | IA | 2026-07-27 | 2026-08-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
16.5455 | * Issued Certificates | IA | 2026-07-27 | 2026-08-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
17.5909 | * Exam Security | IA | 2026-07-27 | 2026-08-05 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
18.6364 | * Activition Account | IA | 2026-08-01 | 2026-08-04 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
19.6818 | LMS Marketing Campain | MAS - IA -MM | 2026-07-25 | 2026-09-01 | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 37.5% | 62.5%
20.7273 | * Design Digital Posters for WhatsApp | IA | 2026-07-25 | 2026-07-29 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
21.7727 | ** Poster Trio Academy Trans 4% | IA | 2026-07-29 | 2026-07-29 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
22.8182 | ** Poster Trio Academy Trans 100% | IA | 2026-07-30 | 2026-07-30 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
23.8636 | ** Poster Goals of Trio Academy | IA | 2026-08-01 | 2026-08-01 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
24.9091 | * Prepare Supervisor Communication Kit | IA | 2026-07-27 | 2026-08-01 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
25.9545 | * Launch Site Competition | IA | 2026-08-01 | 2026-08-05 | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 37.5% | 62.5%
27 | * Announce Best Performing Site | IA | 2026-08-20 | 2026-08-30 | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 37.5% | 62.5%
28.0455 | * Design Digital Certificates & Badges | IA | 2026-08-20 | 2026-08-30 | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 37.5% | 62.5%
29.0909 | Create GIF Signature | IA | 2026-07-27 | 2026-07-30 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
30.1364 | Company Presentation | IA - MM | 2026-07-25 | 2026-08-01 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
31.1818 | على جميع عاملي التغذيه بشركة أي أف أٍس الإلتزام بقوانين وقواعد الصحه والسلامه الغذائيه module(1) | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
32.2273 | أولًا... النظافة الشخصية | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
33.2727 | ثانيًا...أماكن المسموح فيها بالأكل و تناول المشروبات | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
34.3182 | ثالثًا...غسيل اليدين و أهميته | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
35.3636 | رابعًا...التدخين و مواعيده و مكان التدخين | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
36.4091 | خامسًا... في حالة انك تكون مريض | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
37.4545 | سادسًا... استخدام الجوانتي او الجلوفز | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
38.5 | سابعًا... أهمية قياس و تسجيل درجة الحراره | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
39.5455 | ثامنًا... استلام المواد الغذائيه | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
40.5909 | تاسعًا... النظافه | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
41.6364 | عاشرًا... ترتيب الثلاجات و الفريزرات | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
42.6818 | الحادي عشر... مناولة المواد الغذائيه | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
43.7273 | الثاني عشر...صلاحية الخامات او المنتجات | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
44.7727 | الثالث عشر... العينات | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
45.8182 | الرابع عشر...الالتزام بالقانون | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
46.8636 | الخامس عشر... الالتزام المهني | MAS - IA - MM | 2026-07-11 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
47.9091 | الخاتمه | MAS - IA - MM | 2026-07-11 | 2026-07-29 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
48.9545 | Update Product Page: | IA | 2026-08-07 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
50 | * Add Entry Level Programs | IA | 2026-08-07 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
51.0455 | * Add Supervisor Level Programs | IA | 2026-08-07 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
52.0909 | * Add Managerial Level Programs | IA | 2026-08-07 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
53.1364 | Apply Mobile Responsive to Website | IA | 2026-08-07 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
54.1818 | Generate Exam Certificate | IA - MM | 2026-08-09 | 2026-08-14 | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 37.5% | 62.5%
55.2273 | Adapt the System for Exam Questions | IA | 2026-08-09 | 2026-08-10 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
56.2727 | المظهر الشخصى والنظافه الشخصيه: | MAS - IA - MM | 2026-07-11 | 2026-07-12 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 62.5% | 37.5%
57.3182 | الاجراءات المتبعه لاستخدام و معايرة الترمومترات | MAS - IA - MM | 2026-07-17 | 2026-07-18 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 62.5% | 37.5%
58.3636 | اجراء تشغيلى خاص بتتبع حاله حرجه | MAS - IA - MM | 2026-07-17 | 2026-07-18 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 62.5% | 37.5%
59.4091 | اجراء التخلص من منتج به اصابه حشريه | MAS - IA - MM | 2026-07-19 | 2026-07-20 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 62.5% | 37.5%
60.4545 | start implementation | IA | 2026-07-07 | 2026-07-11 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 62.5% | 37.5%
61.5 | Review on every activity line to ensure alignment with agreed upon plan | MAS - MM | 2026-07-07 | 2026-07-21 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 62.5% | 37.5%
62.5455 | Aopproval | MAS | 2026-07-20 | 2026-07-21 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 62.5% | 37.5%
63.5909 | Posting/rollout | MAS - IA | 2026-07-07 | 2026-07-22 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | 62.5% | 37.5%
78.2273 | update skill test | IA | 2026-08-20 | 2026-08-23 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
79.2727 | Design Prepare Exam Photo | IA | 2026-08-24 | 2026-08-25 | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 25% | 75%
80.3182 | Design Entry Level Photo | IA | 2026-08-24 | 2026-08-25 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 75% | 25%
81.3636 | Design Supervisor Level Photo | IA | 2026-08-24 | 2026-08-25 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 75% | 25%
82.4091 | Design Managerial Level Photo | IA | 2026-08-24 | 2026-08-25 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 75% | 25%

## Trio Academy(LMS)
Trio Academy (LMS) — Technical Tasks Plan | [11 empty] | STATUS SUMMARY
S | Trio Academy LMS — Dev | Resp | Start Date | End Date | Implementation | [6 empty] | Done | 159 | 98.76%
[5 empty] | Brainstorming | Plan | Execute | Test | Redeploy | Missing | Done | In progress / Pending | 2 | 1.242%
1 | Purchase LMS Requirements | MAS - MM - F | 2026-07-04 | 2026-07-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Backlog / Not started | 0 | 0%
2 | Upload LMS and Setup on the Server | IA | 2026-07-05 | 2026-07-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Overall completion | 99.38%
3 | Initialize the Full website and Create All Employee Accounts | IA | 2026-07-07 | 2026-07-10 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Total tasks | 161
4 | Upload the full project | IA | 2026-07-16 | 2026-07-16 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
5 | Implement admin resource management system with CRUD and versioning capabilities | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Overall completion | 99.74%
6 | Implement LearningService for course progress tracking and add CourseDetail pages with RTL support | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100% | Total tasks | 153
7 | Implement admin certificate management module including issuance, revocation, and template design capabilities | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
8 | Implement secure exam window with randomization, auto-save, and anti-cheating features | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
9 | Implement secure exam interface with tab-guarding, auto-saving, and anti-cheat security measures | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
10 | Implement core API hooks, TypeScript definitions, and UI components for certificate viewing and exam management pages. | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
11 | Add Arabic and English Certificate assessment hubs with course tracking and exam request functionality | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
12 | Implement learning service and add dashboard and certificate pages | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
13 | Implement Arabic language support and assessment hub for certificate tracking | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
14 | Implement LearningService for course management and dashboard tracking, and add supporting infrastructure configurations | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
15 | Implement certificate page functionality with new API hooks and bilingual support | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
16 | Implement learning dashboard, backend services, and exam progress tracking hooks | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
17 | Implement localized login pages and add utility helpers for ID display and class merging | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
18 | Implement UserService and migration to support company-level username formatting | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
19 | Add development data seeder to initialize catalog and user entities | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
20 | Implement bulk import services and infrastructure for users, departments, and exam security, and update seed data formats. | IA | 2026-07-18 | 2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
21 | Introduce redesigned employee dashboard with navigation header and localized support | IA | 2026-07-19 | 2026-07-19 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
22 | Support certificate template orientation and improve program imagery | IA | 2026-07-20 | 2026-07-20 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
23 | Remove Clerk authentication dependency | IA | 2026-07-20 | 2026-07-20 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
24 | Add PreToolUse hooks configuration to integrate graphify security checks | IA | 2026-07-20 | 2026-07-20 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
25 | Implement core learning infrastructure, exam management, and dashboard services with frontend integration | IA | 2026-07-20 | 2026-07-20 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
26 | Implement ImportService for batch data processing and ReportingService for generating system reports | IA | 2026-07-22 | 2026-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
27 | Implement ImportService for batch data processing and add QuizPlayer component for AR and standard course views | IA | 2026-07-22 | 2026-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
28 | Implement reporting service and manager Excel export functionality with API hooks | IA | 2026-07-22 | 2026-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
29 | Fix: add MANAGERID column with matching collation for FK compatibility | IA | 2026-07-22 | 2026-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
30 | Fix: add raw SQL fallback hotfixes for ManagerId and CareerLevelRaw columns | IA | 2026-07-22 | 2026-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
31 | Maintenance: trigger Dokploy redeploy | IA | 2026-07-22 | 2026-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
32 | Add CareerLevelRaw column to import rows migration | IA | 2026-07-22 | 2026-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
33 | Add admin employee management page with CRUD, bulk import, and credential reporting features | IA | 2026-07-22 | 2026-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
34 | Implement admin employees management page with bulk import and reporting features | IA | 2026-07-22 | 2026-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
35 | Add ManagerId to ApplicationUser, implement import and reporting services, and create employee management page | IA | 2026-07-22 | 2026-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
36 | Implement ReportingService to provide analytics for exams, departments, and course performance | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
37 | Add admin reports page for Arabic localization | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
38 | Implement bilingual employee management and reporting pages for admin dashboard | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
39 | Implement employee management module with API DTOs, administrative UI, and backend services. | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
40 | Implement ReportingService to provide aggregated platform, department, course, and exam security data with caching | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
41 | Add employee management page, implement bulk import functionality, and expose department credential reporting for administrators | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
42 | Implement IMemoryCache service and add auxiliary guard skills | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
43 | Implement admin modules for employees and reporting with bulk import and credential management capabilities | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
44 | Implement comprehensive reporting dashboard with multi-language support and advanced data filtering analytics | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
45 | Implement ReportingService for exam security, overview, department, and course analytics | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
46 | Implement .env configuration loader and DataProtection persistence in Program.cs | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
47 | Implement reporting service and add employee overview page for data visualization | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
48 | Implement ImportService to support batch importing of employees, departments, and job titles via Excel templates | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
49 | Implement comprehensive analytics dashboard with multi-metric reporting, filtering, and data export capabilities | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
50 | Implement Arabic administrative dashboard pages for Reports and Employees management | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
51 | Implement employee management and credential reporting features for both English and Arabic admin dashboards | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
52 | Implement quiz validation logic and create admin management pages for quizzes and exams | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
53 | Implement reporting service and admin dashboard analytics pages | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
54 | Add Quiz management page for admin and localization modules | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
55 | Add quiz management dashboard with bulk import support and Nginx configurations | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
56 | Implement multi-language support with RTL layout and localized Arabic navigation routes | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
57 | Implement reporting service and import service for data analysis and administration | IA | 2026-07-25 | 2026-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
58 | Implement comprehensive administrative reporting dashboard with data analytics and filtering | IA | 2026-07-29 | 2026-07-29 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
59 | Add certificate expiry tracking and implement comprehensive administrative reporting dashboard with export capabilities | IA | 2026-07-29 | 2026-07-29 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
60 | Implement reporting service, DTOs, and controller for system analytics and exam security monitoring | IA | 2026-07-29 | 2026-07-29 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
61 | Implement user management service and API controllers for employee CRUD and administrative operations | IA | 2026-08-03 | 2026-08-03 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
62 | Add Arabic and English employee detail pages with backend service integration | IA | 2026-08-03 | 2026-08-03 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
63 | Add schema migrations for user hierarchy, activity tracking, certificate expiry, and import data enhancements | IA | 2026-08-03 | 2026-08-03 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
64 | Add period-aware admin reports and valid Excel exports | IA | 2026-08-03 | 2026-08-03 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
65 | Implement secure resource viewer with anti-tamper watermarking, audit logging, and content protection controls | IA | 2026-08-04 | 2026-08-04 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
66 | Implement bilingual course platform with Arabic RTL support and Netflix-style navigation components | IA | 2026-08-04 | 2026-08-04 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
67 | Implement import functionality with caching, database indexing, and service extensions | IA | 2026-08-04 | 2026-08-04 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
68 | Add IntroLoadingScreen component and implement Arabic admin employee detail page | IA | 2026-08-04 | 2026-08-04 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
69 | Add Hub page component for Arabic localization | IA | 2026-08-04 | 2026-08-04 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
70 | Implement full Arabic localization for core pages and components including authentication, dashboard, and employee management modules. | IA | 2026-08-04 | 2026-08-04 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
71 | Implement Arabic language support with dedicated layout, header, and navigation components along with a shared course toolbar. | IA | 2026-08-04 | 2026-08-04 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
72 | Add IntroLoadingScreen, setup AR routing, and migrate ManagerId to ApplicationUser | IA | 2026-08-04 | 2026-08-04 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
73 | Add Nginx production/development configurations and implement application setup in Program.cs | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
74 | Implement responsive Logo component with configurable brand variants and sizing | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
75 | Add trio branding assets and update logo copy logic in vite config | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
76 | Implement CourseDetail page with enrollment, video playback, and resource viewing features | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
77 | Implement course detail page and navigation structure with localized components and branding assets | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
78 | Implement certificates and assessments page with branded logo component and associated assets | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
79 | Implement LearningService and add FluentValidation rules for learning modules | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
80 | Implement bilingual exam window with secure proctoring and progress tracking features | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
81 | Implement secure ResourceViewer with dynamic watermarking, audit logging, and anti-tamper protections. | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
82 | Implement secure multilingual exam interface with dynamic routing and quiz player components | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
83 | Implement ExamWindow page with secure proctoring features and bilingual support | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
84 | Implement secure resource viewer with watermark, tamper detection, and audit logging | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
85 | Implement multilingual exam interface with secure navigation and quiz player components | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
86 | Add IntroLoadingScreen and implement Arabic localized admin/employee layouts and i18n configuration | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
87 | Implement CatalogService to manage departments, job titles, and categories with caching support | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
88 | Add backend startup configuration, environment-based settings, and Nginx reverse proxy templates | IA | 2026-08-06 | 2026-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
89 | Add employee learning record detail page with CSV export and notification features | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
90 | Implement HLS-supported video player component with progress tracking and backend integration | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
91 | Implement HLS-compatible video player with progress tracking and playback controls | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
92 | Make admin dashboard and layouts responsive on mobile devices | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
93 | Resolve JSX grid container nesting imbalance in English and Arabic CourseDetail pages | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
94 | Implement course detail page with enrollment, video progress tracking, and resource viewing support | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
95 | Resolve ReferenceError completed is not defined in Arabic CourseDetail | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
96 | Implement course management page for Arabic admin dashboard | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
97 | Implement course-department association and career-based targeting functionality | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
98 | Implement course management entities, validation, and Arabic localized course detail page | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
99 | Add new product catalog pages with program details and filtering functionality | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
100 | Documentation: add documentation for enhanced course progress and video playback features | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
101 | Implement complete multi-language profile management, video progress tracking, and administrative dashboard components | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
102 | Add admin video management page with CRUD operations and Bunny Stream integration | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
103 | Implement comprehensive certificate management system including issuance, revocation, and template customization with RTL support. | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
104 | Implement LearningService and refactor practical tests to skill-based assessment system | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
105 | Implement admin video management interface with CRUD functionality and Bunny Stream integration | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
106 | Implement comprehensive course details page with enrollment, video playback, and responsive layout management | IA | 2026-08-08 | 2026-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
107 | Add ExamSecurityReport component, PaginationBar, and localized Arabic pages for certificates and analytics | IA | 2026-08-09 | 2026-08-09 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
108 | Implement Arabic language support and admin dashboard pages for quizzes, courses, and user management. | IA | 2026-08-09 | 2026-08-09 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
109 | Add migrations for exam session career levels and question counts, and document schema-change requirements in AGENTS.md | IA | 2026-08-10 | 2026-08-10 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
110 | Implement exam session scheduling with career level filtering and configurable question counts | IA | 2026-08-10 | 2026-08-10 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
111 | Maintenance: ignore exam-related files in gitignore | IA | 2026-08-10 | 2026-08-10 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
112 | Implement secure resource viewer with dynamic watermarking, audit tracking, and DRM protection features | IA | 2026-08-10 | 2026-08-10 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
113 | Implement category management, course CRUD, and localized AR hub pages with corresponding backend services and data structures | IA | 2026-08-11 | 2026-08-11 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
114 | Implement AR course detail page with component structure and mobile-responsive test suite | IA | 2026-08-11 | 2026-08-11 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
115 | Implement LearningService for course navigation and tracking, and add ExamSessionCareerLevel unit tests | IA | 2026-08-12 | 2026-08-12 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
116 | Implement CatalogService and initialize dashboard and quiz pages with localization support | IA | 2026-08-12 | 2026-08-12 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
117 | Testing: add unit tests for BunnyLessonVideoPlayer completion logic and progress tracking | IA | 2026-08-12 | 2026-08-12 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
118 | Implement import module for employees, departments, job titles, and bilingual quizzes | IA | 2026-08-15 | 2026-08-15 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
119 | Update light mood | IA | 2026-08-16 | 2026-08-16 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
120 | Update reports of employees to Cost Center | IA | 2026-08-18 | 2026-08-18 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
121 | Fix exam upload | IA | 2026-08-19 | 2026-08-19 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
122 | Update quiz questions | IA | 2026-08-19 | 2026-08-19 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
123 | Update progress bar | IA | 2026-08-19 | 2026-08-19 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
124 | Update course window in ar | IA | 2026-08-20 | 2026-08-20 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
125 | Update Progress bar Logic | IA | 2026-08-20 | 2026-08-20 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
126 | Fix exam | IA | 2026-08-22 | 2026-08-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
127 | Fix: localize CareerPathCard for Arabic and fix RTL layout and strings | IA | 2026-08-22 | 2026-08-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
128 | Fix: integrate react-markdown and remark-gfm for tables, punctuation, and full markdown rendering | IA | 2026-08-22 | 2026-08-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
129 | Fix ai chat copilot | IA | 2026-08-22 | 2026-08-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
130 | Fix: enhance AI chatbot with direct LLM fallback, intelligent domain knowledge engine, and bilingual UI | IA | 2026-08-22 | 2026-08-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
131 | Resolve 400 bad request, fix Arabic UTF-8 encoding, and remove hardcoded mock managers | IA | 2026-08-22 | 2026-08-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
132 | Maintenance: wire AI and ERB environment variables to docker-compose and .env.example | IA | 2026-08-22 | 2026-08-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
133 | Cleanly separate Arabic and English employee names and add cost center filter | IA | 2026-08-22 | 2026-08-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
134 | Fix: make admin reports hub, tabs, and sub-reports fully responsive | IA | 2026-08-22 | 2026-08-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
135 | Integrate AI Copilot with dynamic role orchestration, executive insights, career pathing, and proctoring anomaly scoring | IA | 2026-08-22 | 2026-08-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
136 | Add Tracking employee loging everyday | IA | 2026-08-22 | 2026-08-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
137 | Update skill test | IA | 2026-08-22 | 2026-08-22 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
138 | Merge branch: Copilot streaming and latency | IA | 2026-08-23 | 2026-08-23 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
139 | Stream copilot replies over SSE to cut perceived latency | IA | 2026-08-23 | 2026-08-23 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
140 | Update | IA | 2026-08-24 | 2026-08-24 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
141 | Merge branch: Copilot streaming and latency | IA | 2026-08-24 | 2026-08-24 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
142 | Fix recommends real courses from your Products page, personalized by each user's career level, job title, and department. | IA | 2026-08-24 | 2026-08-24 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
143 | Update logo | IA | 2026-08-24 | 2026-08-24 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
144 | Merge branch: Exam camera mic monitoring | IA | 2026-08-25 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
145 | Live camera/mic presence indicator during exams | IA | 2026-08-25 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
146 | Fix: trust upstream proxy IP for rate limiting and raise api burst limit | IA | 2026-08-25 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
147 | Fix: group exam violations by enum so the query translates to SQL | IA | 2026-08-25 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
148 | Merge branch: Copilot streaming and latency | IA | 2026-08-25 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
149 | Add Exam Attendance tab filtered by cost center | IA | 2026-08-25 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
150 | Merge branch: Copilot streaming and latency | IA | 2026-08-25 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
151 | Fix: use AdminOnly policy for AiController and ErbSyncController | IA | 2026-08-25 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
152 | Merge branch: Copilot streaming and latency | IA | 2026-08-25 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
153 | Fix: connect ai-service to prod network and set default production endpoint | IA | 2026-08-25 | 2026-08-25 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
154 | Merge branch: Exam camera mic monitoring | IA | 2026-08-25 | 2026-08-29 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
155 | Fix track loginng | IA | 2026-08-25 | 2026-08-29 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
156 | Create Certificate Template for Food Safety | IA | 2026-09-06 | 2026-09-06 | TRUE | TRUE | TRUE | FALSE | FALSE | 40% | 60%
157 | Optimize Certificate Page and Backend | IA | 2026-09-06 | 2026-09-06 | TRUE | TRUE | FALSE | FALSE | FALSE | 60% | 40%
158 | In the admin Reports area, both exam tabs now drill into the graded paper: | IA | 2026-09-06 | 2026-09-07 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
159 | Exam Attendance — expand an employee row, and each exam they sat gets a Review answers button (one per attempt when they took it more than once). | IA | 2026-09-06 | 2026-09-07 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
160 | Exam Security — each attempt row gets its own Review answers button. | IA | 2026-09-06 | 2026-09-07 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%
161 | Admin pass/fail status override, retake grant, and threshold recalculation | IA | 2026-09-06 | 2026-09-07 | TRUE | TRUE | TRUE | TRUE | TRUE | 0% | 100%